## Calculation
| Start Date | End Date | Days | total Hours | Hrs | Min | Seconds
Period
Total Time | 2012-05-09 | 2012-05-29 | 15 | 120 | 120 | 15 | 15
Billable Time | 2012-05-09 | 2012-05-29 | 15 | 120 | 40 | 11 | 13
Amyn Essa | 20% |  |  | Planned | 40
Raheel Rupani | 16% |  |  | Actual | 70 |  |  | Resource utilization
Nooruddin Surani | 39% |  |  | Slipage | -30 |  |  | RR |  | 67 | -33
Jahangir Sachwani | 10% | [6 empty] | NS |  | 86 | -14
Amin Safri | 15% | [6 empty] | KW |  | 132 | 32
| 100% | [6 empty] | JS |  | 30 | -70
[8 empty] | HA |  | 95 | -5
Marketing | 18% | [6 empty] | UB |  | 17 | -83
Alliance Team | 16%
Enginnering | 15% |  |  | Cost 1 | 23281
Research and Development | 10% |  |  | Cost 2 | 35056
Quality | 10% |  |  | Cost 3 | 22464
PMO | 9% |  |  | Cost 4 | 30637
Others | 22% |  |  | Cost 5 | 36212
100%
Critical Task 1 | 70% | 10 | 1 |  | Jan | 429
Critical Task 2 | 59% | 3 | 2 |  | Feb | 392
Critical Task 3 | 74% | 5 | 3 |  | Mar | 391
Critical Task 4 | 59% | 6 | 4 |  | Apr | 448
Critical Task 5 | 87% | 2 | 5 |  | May | 455
[5 empty] | Jun | 399
Overallocated Resources
Resource |  | %
Raheel |  | 57
Jahangir |  | 67
Nooruddin |  | 65
Amyn |  | 35
Sample Risk 1 | 10
Sample Risk 2 | 10
Sample Risk 3 | 2
Sample Riks 4 | 4
Sample Risk 5 | 6
|  | Planned | Target | Actual
| User Requirement Analysis | 100 | 100 | 89 | 89% | 11%
| Solution Design | 100 | 100 | 93 | 93% | 7%
| Solution Development | 100 | 70 | 62 | 88.57% | 11.43%
| Solution Testing | 100 | 50 | 50 | 100% | 0%
| Scanning of Document | 100 | 40 | 30 | 75% | 25%
Task
| Not Started | 4
| In progress | 5
| Completed | 6
15
Average Line
| Jan | 10000 |  | 32189.0238
| Feb | 11600 | 16 | 32189.0238
| Mar | 13108 | 13 | 32189.0238
| Apr | 14812.04 | 13 | 32189.0238
| May | 17181.9664 | 16 | 32189.0238
| Jun | 20446.54 | 19 | 32189.0238
| Jul | 23309.0556 | 14 | 32189.0238
| Aug | 25873.0517 | 11 | 32189.0238
| Sep | 28977.8179 | 12 | 32189.0238
| Oct | 33614.2688 | 16 | 32189.0238
| Nov | 40337.1226 | 20 | 32189.0238
| Dec | 45984.3197 | 14 | 32189.0238
Project Metrics
Estimates |  |  |  |  | Actual |  |  |  | Top Critical Tasks |  |  |  | Overallocated Resources |  |  | Top Open Risk
Cost Estimates |  |  | 394500 |  | Actual Cost |  | 3443933 |  | Task | Days Left |  | % | Resource |  | % | Sample Risk 1 | 10
Revenue Estimates |  |  | 4341730 |  | Earned Revenue |  | 178181 |  | Critical Task 1 | 10 | 70% | 70% | Raheel | 57 | 57hrs | Sample Risk 2 | 10
Taxes |  |  | 16075 |  | Cost Plus Revenue |  | 131550 |  | Critical Task 2 | 3 | 59% | 59% | Jahangir | 67 | 67hrs | Sample Risk 3 | 2
Percent Budget Spent |  |  | 87.3% |  | Percent Time Elapsed |  | 53.3% |  | Critical Task 3 | 5 | 74% | 74% | Nooruddin | 65 | 65hrs | Sample Riks 4 | 4
Default Markup |  |  | 30% |  | Percent Complete |  | 90.24% |  | Critical Task 4 | 6 | 59% | 59% | Amyn | 35 | 35hrs | Sample Risk 5 | 6
Formulas:
Start Date = [Start Date, row above]
End Date = [Start Date]+RANDBETWEEN(10,20)
End Date = [End Date, row above]
Days = NETWORKDAYS([Start Date],[End Date])

## dashboard
PROJECT DASHBOARD
58 % Completed
|  | Phase 1 |  |  |  | Phase 2 |  |  |  |  | Phase 3 |  |  |  | Phase 4 |  |  | Phase 5
| Total Work | [7 empty] | Actual Work | [6 empty] | Remaining Work | [5 empty] | Earned Value
| 400 | [7 empty] | 232 | [6 empty] | 168 | [5 empty] | 116000
| 50 | [7 empty] | 29 | [6 empty] | 21
58%
| 200000 | [7 empty] | 127600 | [6 empty] | 72400
| Estimates | [6 empty] | Actuals | [5 empty] | Top Critical Tasks | [5 empty] | Top Overallocated Resources |  |  |  |  | Top Risk
| Cost Estimates |  |  | 394500 |  |  |  | Actual Cost |  |  | 3443933 |  |  | Task |  |  | % Complete | Days Left |  | Name |  |  |  | Hrs | Risk 1 | 10
| Revenue Estimates |  |  | 4341730 |  |  |  | Earned Revenue |  |  | 178181 |  |  | Critical Task 1 |  |  | 70% | -5 |  | Raheel | 57 |  |  | 57hrs | Risk 2 | 10
| Taxes |  |  | 16075 |  |  |  | Cost Plus Revenue |  |  | 131550 |  |  | Critical Task 2 |  |  | 59% | 6 |  | Jahangir | 67 |  |  | 67hrs | Risk 3 | 2
| % Budgest Spent |  |  | 87.3% |  |  |  | Percent Time Elapsed |  |  | 53.3% |  |  | Critical Task 3 |  |  | 74% | 8 |  | Nooruddin | 65 |  |  | 65hrs | Risk 4 | 4
| Defualt Markup |  |  | 30% |  |  |  | Percent Complete |  |  | 90.24% |  |  | Critical Task 4 |  |  | 59% | 4 |  | Amyn | 35 |  |  | 35hrs | Risk 5 | 6
| Risk Matrix | [11 empty] | Tasks | [8 empty] | Cost
| Impact |  | Rare |  | Unlikey |  | Possible |  | Likely |  | Almost
|  |  | 0 - 20 % |  | 20 - 40% |  | 40 - 60% |  | 60 - 80% |  | > 80%
| Catastropic |  | 2 |  | 2 |  | 1 |  | 2 |  | 1
| Major |  | 1 |  | 0 |  | 1 |  | 0 |  | 2
| Moderate |  | 0 |  | 1 |  | 0 |  | 1 |  | 1
| Minor |  | 1 |  | 2 |  | 1 |  | 1 |  | 2
| Insignificant |  | 0 |  | 1 |  | 0 |  | 0 |  | 2
| Summary Wise Progress as today | [19 empty] | Top Cost
[10 empty] | Planned |  | Actual
| Task Group | [5 empty] | Progress | [11 empty] | % Complete
| + User Requirement Analysis | [17 empty] | 89%
| + Solution Design | [17 empty] | 93%
| + Solution Development | [17 empty] | 88.57% |  | Monthly Hours Work
| + Solution Testing | [17 empty] | 100%
| + Scanning of Document | [17 empty] | 75%